## Capability Catalogue
# | Stage | Category | Capability | Description | AI/ML Technique | Data Inputs | Systems/Tools | Value/Benefit | Value Type | Human Role | Human Role Description | Related Capabilities
1 | 01 Demand & intake | Lifecycle | Capture & structure demand | Turns any incoming request into a clean, complete, structured demand record | LLM (NLU + generation); document parsing | Emails, Teams messages, intake forms, tickets | Outlook/Teams, SharePoint forms, ITSM; writes ADO/Planview | Faster, cleaner intake; less back-and-forth | Speed | Human approves | Confirms scope before it enters the portfolio | Classify & route; Capacity check
2 | 01 Demand & intake | Lifecycle | Classify & route | Classifies demand by type, domain, risk and funding and routes it; flags duplicates | Text classification; retrieval (embeddings) | Demand taxonomy, org/domain directory, historical demand corpus | ADO/Planview, identity directory | Triage in minutes; duplicates caught early | Speed | Human approves | Owns final routing and priority | Capture & structure; Capacity check
3 | 01 Demand & intake | Lifecycle | Capacity check | Tests new demand against capacity, skills and roadmap for an early feasibility signal | Forecasting ML; optimization | Capacity & resource pool, skills data, roadmap | Planview resource management | Realistic commitments; less over-loading | Risk/Control | Human approves | Decides what to commit | Classify & route; Resource levelling
4 | 01 Demand & intake | Lifecycle | Business-case draft | Assembles a first-cut business case from the demand and comparable past work | LLM generation; retrieval | Demand record, comparable project actuals, finance benchmarks | Planview, finance/ERP, SharePoint | Faster initiation; consistent cases | Speed | Human directs | Owns the case and the numbers | Capture & structure; Estimate from history
5 | 02 Estimate & shape | Lifecycle | Estimate from history | Sizes effort, cost and duration from comparable completed work, with a confidence range | Forecasting / regression ML; retrieval | ADO history, Planview actuals, prior-project effort/cost repository | ADO, Planview | More accurate estimates; fewer overruns | Cost/Effort | Human directs | Calibrates and owns the estimate | Business-case draft; Reconcile plans
6 | 02 Estimate & shape | Lifecycle | Challenge the estimate | Stress-tests an estimate for optimism bias and missing scope | LLM reasoning; analytics | Estimate, historical actuals, risk-factor register | ADO, Planview | Estimate integrity; fewer surprises | Risk/Control | Human directs | Decides whether to revise | Estimate from history
7 | 02 Estimate & shape | Lifecycle | Re-estimate triggers | Watches scope and actuals and flags when a re-baseline is warranted | Anomaly detection | Live scope (ADO), actuals & timesheets | ADO, timesheets | Forecasts stay honest | Risk/Control | Human approves | Approves the re-baseline | Critical-path view; Burn & forecast
8 | 03 Plan & schedule | Lifecycle | Reconcile plans | Keeps plans in sync across tools and flags divergence before steering | Data integration; entity matching | ADO sprints, Planview milestones, MS Project, vendor plans | ADO, Planview, MS Project, vendor tools | Plans you can trust; less manual rework | Cost/Effort | Human approves | Resolves the conflicts | Critical-path view; Multi-vendor status
9 | 03 Plan & schedule | Lifecycle | Critical-path view | Continuously computes critical path, float and conflicts and explains the end-date driver | Graph analytics; scheduling | Plan, task dependencies, actuals | ADO, Planview | Slippage foreseen early | Speed | Human directs | Acts on the bottleneck | Reconcile plans; Sense dependencies
10 | 03 Plan & schedule | Lifecycle | Re-plan scenarios | Generates re-plan options (crash, de-scope, add capacity) with cost-date trade-offs | Optimization / solver; LLM | Plan, resource roster, cost rates, constraints | Planview, finance | Faster recovery from slips | Speed | Human directs | Chooses the trade-off | Critical-path view; Resource levelling
11 | 03 Plan & schedule | Lifecycle | Resource levelling | Proposes assignment changes to resolve over-allocation and skills gaps | Optimization / solver | Resource & capacity, skills, allocations | Planview | Better utilisation; less burnout | Cost/Effort | Human directs | Owns people decisions | Capacity check; Re-plan scenarios
12 | 04 Dependencies | Lifecycle | Sense dependencies | Discovers dependencies automatically from work links, architecture and comms | Knowledge graph; NLP; retrieval | Work-item links, architecture/CMDB, Teams comms, component registry | ADO, CMDB, Teams | The top slippage cause caught early | Risk/Control | Human monitors | Curates the dependency graph | Critical-path view; Cross-programme impact; Risk sensing
13 | 04 Dependencies | Lifecycle | Chase commitments | Tracks cross-team commitments and nudges owners; escalates threats to the critical path | Workflow automation; LLM | Dependency log, owner directory, status feeds | ADO, Teams/email | Coordination toil removed | Cost/Effort | Human approves | Sets escalation rules | Sense dependencies; Status reporting
14 | 04 Dependencies | Lifecycle | Cross-programme impact | Computes the ripple across other programmes sharing the same assets | Knowledge graph analytics | Portfolio dependency graph, shared-asset registry, change calendar | Planview, ITSM, ADO | Collisions avoided | Risk/Control | Human monitors | Reviews impact, decides sequencing | Sense dependencies; Collision detection
15 | 05 Config & environments | Lifecycle | Drift detection | Reconciles records against what is actually deployed and flags drift | Anomaly detection; config compare | CMDB, environment registries, live deploy state (pipelines/IaC) | CMDB/ITSM, ADO pipelines, IaC | Fewer failed changes | Risk/Control | Human monitors | Acts on flagged drift | Baseline reconcile; Release-readiness
16 | 05 Config & environments | Lifecycle | Baseline reconcile | Maintains release baselines and verifies the right versions are bundled | Config analysis; rules | ADO repos & pipelines, release definitions, artifact registry | ADO, artifact registry | Release integrity | Risk/Control | Human approves | Confirms the baseline | Drift detection; Deployment orchestration
17 | 05 Config & environments | Lifecycle | Records hygiene | Proposes configuration-record updates from observed reality | Anomaly detection; LLM | CMDB, discovery tooling, observed state | CMDB/ITSM, discovery tools | Trustworthy source of record | Quality | Human approves | Approves every write | Drift detection
18 | 06 Build & deploy | Lifecycle | Deployment orchestration | Drives the deployment runbook across environments and teams; checks pre-conditions | Workflow automation; orchestration | Pipelines, deployment tools, runbooks, change records | ADO pipelines, deploy tools, SharePoint, ITSM | Cutover toil and errors down | Cost/Effort | Human approves | Holds go/no-go on production steps | Release-readiness; Rollback readiness; Cutover comms
19 | 06 Build & deploy | Lifecycle | Release-readiness | Verifies every go-live precondition and produces an evidence-backed go/no-go | Multi-agent orchestration; rules | Test results, change approval, config state, ops-readiness | ADO Test, ITSM, CMDB | Safer, faster go/no-go | Risk/Control | Human approves | Makes the go/no-go call | Test execution; Drift detection; Change-record drafting; Readiness validation
20 | 06 Build & deploy | Lifecycle | Rollback readiness | Prepares and validates the rollback plan before cutover | Workflow automation; verification | Release definition, environment state, backup/restore | ADO, deploy tools, backup systems | Blast-radius control | Risk/Control | Human approves | Confirms rollback is viable | Deployment orchestration
21 | 06 Build & deploy | Lifecycle | Cutover comms | Runs the cutover bridge: live status, step tracking, stakeholder updates | LLM generation; eventing | Deployment status feed, stakeholder directory | Deploy tools, Teams | Calmer, faster cutovers | Speed | Human monitors | Owns decisions on the bridge | Deployment orchestration; Status reporting
22 | 06 Build & deploy | Lifecycle | Runbook drafting | Drafts and maintains deployment runbooks from the change and prior runbooks | LLM generation; retrieval | Change record, prior runbooks, architecture docs | SharePoint, ADO | Preparation time down | Cost/Effort | Human directs | SME reviews the runbook | Deployment orchestration
23 | 07 Test & quality | Lifecycle | Test generation | Derives test cases from requirements and code changes, with traceability | LLM; code analysis | Requirements/stories, code diffs, traceability | ADO, repos | Coverage up; design time down | Quality | Human directs | Reviews critical-path tests | Test data on demand; Test execution; Traceability
24 | 07 Test & quality | Lifecycle | Test data on demand | Provisions compliant masked/synthetic data matched to test needs | Synthetic data generation; data masking | Prod schema (masked), data-classification policy, test envs | Test-data tools, test environments | A top time-to-market bottleneck removed | Speed | Human approves | Privacy sign-off | Test generation; Test execution
25 | 07 Test & quality | Lifecycle | Defect triage | Clusters, dedups, prioritises and routes defects; hints root cause | Clustering; classification; retrieval | Defect backlog, code-ownership map, historical defects | ADO, repos | Triage time down; release risk visible | Quality | Human approves | Confirms high-severity calls | Quality gate; Status reporting
26 | 07 Test & quality | Lifecycle | Security testing | Runs continuous in-pipeline security testing, triages findings, drafts fixes | DAST/SAST scanners + LLM triage | CI/CD pipeline, app endpoints, vulnerability database | Pipeline, security tools, ITSM | Security off the critical path (TTM) | Risk/Control | Human approves | Signs off exploitable findings | Quality gate; Release-readiness
27 | 07 Test & quality | Lifecycle | Test execution | Selects and runs the right impact-based suite; reports results with failure analysis | Test automation; LLM analysis | Test suites, change-to-test impact map, CI results | ADO Test, CI | Test cycle time down | Speed | Human approves | Accepts the test outcome | Test generation; Release-readiness
28 | 07 Test & quality | Lifecycle | Traceability | Maintains the live requirement-test-defect matrix, audit-ready | Knowledge graph; linking | Requirements, tests, defects (linked) | ADO | Audit evidence; coverage gaps visible | Quality | Human directs | Reviews coverage | Test generation; Quality gate
29 | 07 Test & quality | Lifecycle | Quality gate | Judges whether quality thresholds are met for release and explains the gaps | Rules + LLM reasoning | Test results, coverage, quality-threshold policy | ADO, quality tools | Objective, explained release gate | Risk/Control | Human approves | Owns the gate decision | Defect triage; Security testing; Release-readiness
30 | 08 Release & change | Lifecycle | Change-record drafting | Auto-authors the change record (plan, backout, evidence) from delivery artefacts | LLM generation; retrieval | Release & test evidence, deployment plan, ITSM schema | ADO, ITSM | Hours of admin per change saved | Cost/Effort | Human approves | Owns the submitted record | Change-risk scoring; Release-readiness
31 | 08 Release & change | Lifecycle | Change-risk scoring | Scores change risk and blast radius and recommends the path | ML classification; analytics | Historical change outcomes, CMDB dependencies, config, calendar | ITSM, CMDB | CAB load down; low-risk change faster | Risk/Control | Human monitors | Reviews or overrides the score | Change-record drafting; Collision detection
32 | 08 Release & change | Lifecycle | CAB prep | Assembles the CAB pack, checks calendar conflicts, pre-answers likely questions | LLM generation; retrieval | Change set, change calendar, CAB policy, prior Q&A | ITSM | CAB preparation toil removed | Cost/Effort | Human approves | Chairs and decides at CAB | Change-record drafting; Collision detection
33 | 08 Release & change | Lifecycle | Collision detection | Finds clashing changes on shared assets and freeze windows | Graph analytics; rules | Change calendar, shared-asset registry, freeze rules | ITSM, CMDB | Avoided incidents | Risk/Control | Human approves | Decides on the clash | Cross-programme impact; Change-risk scoring
34 | 08 Release & change | Lifecycle | Audit evidence | Continuously assembles the who/what/when/approval trail, regulator-ready | Knowledge graph; immutable logging | Change-lifecycle events, approvals | ITSM, log store | Audit cost down; compliance up | Risk/Control | Human monitors | Attests to the record | Change-record drafting
35 | 09 Ops readiness | Lifecycle | Readiness validation | Checks readiness criteria and reports gaps before go-live | Rules + LLM | Readiness criteria, monitoring config, support model, KT | ITSM, monitoring, SharePoint | Post-go-live incidents avoided | Risk/Control | Human approves | Owns the readiness sign-off | Release-readiness; Monitoring setup
36 | 09 Ops readiness | Lifecycle | Handover & KT | Generates the support runbook, known-error notes and KT pack for run teams | LLM generation; retrieval | Delivery artefacts, known-errors, runbooks, knowledge base | SharePoint, ITSM, KB | Smoother handover; better early-life support | Quality | Human directs | Run team reviews | Runbook drafting; Knowledge & onboarding
37 | 09 Ops readiness | Lifecycle | Monitoring setup | Proposes the alerts and dashboards a change needs from its components and SLOs | LLM; config generation | Component inventory, SLOs | Observability platform | Day-one observability | Quality | Human directs | SRE reviews | Readiness validation
38 | Always-on · Risk & issues | Always-on | Risk sensing | Surfaces emerging risks from delivery signals before humans log them | Anomaly detection; NLP sentiment; retrieval | Velocity & build failures, comms sentiment, dependency breaks | ADO, Teams, CI | Risks caught weeks earlier | Risk/Control | Human monitors | Accepts and owns mitigation | Sense dependencies; Status reporting; Issue resolution
39 | Always-on · Risk & issues | Always-on | Mitigation tracking | Tracks mitigation actions to closure; flags risks with no live mitigation | Workflow automation | RAID log, action owners, status | ADO / SharePoint RAID | RAID hygiene maintained | Cost/Effort | Human approves | Owns mitigation decisions | Risk sensing
40 | Always-on · Risk & issues | Always-on | Issue resolution | Assembles context and similar past issues; proposes a resolution path | Retrieval; LLM reasoning | Issue log, similar past issues, knowledge base | ADO, KB | Issue cycle time down | Speed | Human directs | Decides the resolution | Risk sensing; Knowledge & onboarding
41 | Always-on · Budget & cost | Always-on | Burn & forecast | Reconciles actuals, tracks burn vs plan, drafts the forecast and variance narrative | Forecasting ML; LLM generation | Finance/ERP actuals, timesheets, vendor invoices, Planview financials | Finance/ERP, timesheets, Planview | Finance cycle time and accuracy up | Cost/Effort | Human directs | Commits the forecast | Re-estimate triggers; Invoice & PO match
42 | Always-on · Budget & cost | Always-on | Invoice & PO match | Matches vendor invoices to POs, SOWs and delivered work; flags discrepancies | Document parsing; matching | Invoices, POs, SOWs, delivered-work records | Finance/ERP, PO system | Leakage and AP toil down | Cost/Effort | Human approves | Approves disputes | Burn & forecast; SLA tracking
43 | Always-on · Budget & cost | Always-on | Capex / opex | Classifies spend as capex/opex against policy, with evidence | Classification; rules | Spend records, capex/opex policy, project structure | Finance/ERP | Finance compliance | Risk/Control | Human directs | Finance signs off | Burn & forecast
44 | Always-on · Vendor coordination | Always-on | Status normaliser | Ingests each vendor's reports in their own format and unifies them into one view | LLM extraction; document parsing | Vendor status reports (varied formats), shared boards, SLA defs | Vendor tools, shared boards | The multi-vendor integration tax removed | Cost/Effort | Human monitors | Validates vendor self-reporting | Status reporting; SLA tracking
45 | Always-on · Vendor coordination | Always-on | SLA tracking | Tracks vendor SLAs and SOW commitments; flags breaches and at-risk obligations | Rules; analytics | Contracts/SOWs, delivery metrics, SLA thresholds | Contract store, delivery data | Vendor accountability | Risk/Control | Human approves | Owns commercial calls | Status normaliser; Invoice & PO match
46 | Always-on · Vendor coordination | Always-on | Vendor onboarding | Runs the access, compliance and setup checklist when a supplier joins or leaves | Workflow automation | Identity & access systems, compliance checklist | IAM, ITSM | Onboarding speed and security | Risk/Control | Human approves | Approves access grants | SLA tracking
47 | Always-on · Reporting & comms | Always-on | Status reporting | Synthesises live data into audience-tuned reports on cadence or on demand | LLM generation; retrieval; multi-agent orchestration | ADO, Planview, finance, RAID (unified read) | ADO, Planview, finance, RAID; outputs PPT/Power BI/Teams | The single biggest time sink returned | Cost/Effort | Human approves | Owns the RAG call and the message | Pulls from nearly all use cases
48 | Always-on · Reporting & comms | Always-on | Exec narrative | Drafts the 'so what' narrative and pre-empts likely exec questions | LLM generation | Status history, prior exec questions | BI, SharePoint | Exec prep time and message quality up | Cost/Effort | Human directs | Owns the message | Status reporting
49 | Always-on · Reporting & comms | Always-on | Meeting actions | Captures decisions and actions and tracks them to closure across tools | Speech-to-text; LLM; workflow | Meeting transcripts, action tracker | Teams, ADO/Planner | Follow-through up; admin down | Cost/Effort | Human approves | Confirms actions and owners | Status reporting
50 | Always-on · Reporting & comms | Always-on | Comms tailoring | Adapts the same update to each audience's concerns and channel | LLM generation | Core update, stakeholder profiles, channels | Email, Teams | Comms load down; alignment up | Cost/Effort | Human directs | Approves external comms | Exec narrative; Status reporting
51 | Always-on · Knowledge & artefacts | Always-on | Artefact sync | Keeps artefacts consistent and current across tools; answers 'where is the latest X' | Knowledge graph; retrieval | Cross-tool artefacts (Teams, SharePoint, Planview, ADO) | Teams, SharePoint, Planview, ADO | Rework down; audit-ready | Quality | Human approves | Governs cross-tool writes | Knowledge & onboarding; Status reporting
52 | Always-on · Knowledge & artefacts | Always-on | Knowledge & onboarding | A living, queryable knowledge base that answers delivery questions and speeds onboarding | RAG + embeddings; LLM | Project-artefact corpus, skills data, onboarding guides | SharePoint, ADO, Teams, KB | Onboarding time down; knowledge retained | Cost/Effort | Human directs | Validates sourced answers | Artefact sync; Issue resolution

## Stage Summary
Stage | Category | Capability Count
01 Demand & intake | Lifecycle | 4
02 Estimate & shape | Lifecycle | 3
03 Plan & schedule | Lifecycle | 4
04 Dependencies | Lifecycle | 3
05 Config & environments | Lifecycle | 3
06 Build & deploy | Lifecycle | 5
07 Test & quality | Lifecycle | 7
08 Release & change | Lifecycle | 5
09 Ops readiness | Lifecycle | 3
Always-on · Risk & issues | Always-on | 3
Always-on · Budget & cost | Always-on | 3
Always-on · Vendor coordination | Always-on | 3
Always-on · Reporting & comms | Always-on | 4
Always-on · Knowledge & artefacts | Always-on | 2
Total |  | 52

## Value & Human Role
Value Type | Count | Human Role | Count
Speed | 9 | Human approves | 27
Risk/Control | 19 | Human directs | 17
Cost/Effort | 17 | Human monitors | 8
Quality | 7 | Total | 52
Total | 52

## Agent Coordination Patterns
Pattern | How it works | Example | Why it matters
Orchestrated | A lead agent breaks a goal into steps and delegates to specialists | Release-readiness pulls the test, config, change and ops agents | One goal, many agents, a single owner of the outcome
Sequential handoff | Work flows from one agent to the next along the value chain | Demand -> estimate -> plan | Each stage starts from clean, complete inputs
Shared context | Agents coordinate through one shared source of truth, not point-to-point calls | All agents read/write the delivery knowledge graph | No integration spaghetti; value compounds
Event-triggered | One signal fans out to the agents that care about it | A failed build alerts the risk, planning and reporting agents | The system reacts in seconds, not at the next standup

## Human-Agent Control Modes
Mode | Posture | The Agent | The Person | Where it fits
Human directs | At the wheel | Drafts, analyses and suggests | Decides and acts | Business cases, estimates, exec narrative
Human approves | At the gate | Does the work, then waits | Signs off before it takes effect | Change records, deployments, test data
Human monitors | On the loop | Acts within agreed limits | Watches and can step in | Status reporting, drift & risk sensing
Exception escalation | Hand-back | Recognises the edge of its remit | Takes the unusual decision | Anything outside the agreed bounds
Principle | The judgement, the relationships and the accountability stay human. The toil does not.

## Legend & Building Blocks
VALUE LEVER
Value Lever | Description
Speed | Faster time-to-market / cycle time / lead time
Quality | Higher quality, fewer escaped defects, better evidence
Cost/Effort | Less manual effort and toil; freed capacity
Risk/Control | Lower risk, stronger control, audit and compliance
INTERACTION MODE
Interaction Mode | Description
Human directs | Agent assists; the person decides and acts (in the loop)
Human approves | Agent acts, then waits for sign-off before it takes effect (at the gate)
Human monitors | Agent acts within agreed limits; the person can intervene (on the loop)
TECH (common building blocks)
Tech | Description
LLM (NLU + generation) | Understands and writes natural language (records, reports, drafts)
Retrieval (RAG + embeddings) | Finds and grounds answers in your own documents and history
Knowledge graph | Connects entities and relationships across the delivery estate
Forecasting / ML | Estimates, predicts and detects anomalies from historical data
Workflow automation | Takes governed actions in systems via APIs
Multi-agent orchestration | Coordinates several specialist agents toward one goal
Synthetic data + masking | Creates compliant, realistic test data without exposing real PII
Note | No fabricated benefit figures: value is shown qualitatively. The quantified case is a separate value-model iteration.